## Main
| Task |  |  | Tasks
Manager
|  |  | Timeline |  | Reminders
User Information |  |  |  | Reports
| First name: | Aziz
| Last Name: | Rawahi
| Employee ID: | mu42663
Modified by:
Enter your details

## Tasks
Calculated Cells
Entered Values
Tasks
| Task | Start Date | Due Date | Days Left | Progress | Status | Priority | Dependency 1 | Dependency 2 | Priority | Number of Dependants | Description | Not Started # | In Progress # | Overdue # | Task | Due Date | Progress | Severity | Rank Initial | Rank Final | Task | Reminders | Old |  | New |  |  | Old Sort | A | New Index | --- | 1
1 | Kaeser air comp. project | 2007-02-17 | 2007-06-03 | -6998 | 100% | 4 |  | 1 | 1 | 5 | 0 | New Kaeser air compressors installed in TF $ MA | 0 | 0 | 0 | Kaeser air comp. project | 2007-06-03 | 100% | P3 |  | 0 | Kaeser air comp. project |  | 1 | 1 | 1 | 1 | 1 | Kaeser air comp. project | Kaeser air comp. project | 1 | Kaeser air comp. project | 2
2 | TF Safeguarding Project | 2007-06-28 | 2007-09-11 | -6898 | 0% | 2 | 1 | 1 | 1 | 3 | 0 | New HAIMA logic will be implemented | 1 | 0 | 1 | TF Safeguarding Project | 2007-09-11 | 0% | P1 | 2 | 1 | TF Safeguarding Project | This task was due 6898 days ago | 1 | 1 | 1 | 1 | 2 | KOS upgrade | KOS upgrade | 2 | KOS upgrade | 3
3 | Watch room upgrade | 2007-08-02 | 2007-09-22 | -6887 | 77% | 3 | 1 | 1 | 1 | 4 | 0 | Upgrading fire station control room | 0 | 1 | 2 | Watch room upgrade | 2007-09-22 | 77% | P2 | 3 | 2 | Watch room upgrade | This task was due 6887 days ago | 1 | 1 | 1 | 1 | 3 | Rawahi new Mawalem Home | Rawahi new Muscat Home | 3 | Rawahi new Muscat Home | 4
4 | KOS upgrade | 2007-08-13 | 2008-02-24 | -6732 | 64% | 3 | 2 | 1 | 1 | 2 | 0 | Metering system upgrade by FMC | 0 | 2 | 3 | KOS upgrade | 2008-02-24 | 64% | P0 | 4 | 3 | KOS upgrade | This task was due 6732 days ago | 1 | 1 | 1 | 1 | 4 | TF Safeguarding Project | TF Safeguarding Project | 4 | TF Safeguarding Project | 5
5 | [5 empty] | 1 |  | 1 |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 5 | Watch room upgrade | Watch room upgrade | 5 | Watch room upgrade | 6
6 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 6 |  |  | 6 |  | 7
7 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 7 |  |  | 7 |  | 8
8 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 8 |  |  | 8 |  | 9
9 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 9 |  |  | 9 |  | 10
10 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 10 |  |  | 10 |  | 11
11 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 11 |  |  | 11 |  | 12
12 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 12 |  |  | 12 |  | 13
13 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 13 |  |  | 13 |  | 14
14 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 14 |  |  | 14 |  | 15
15 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 15 |  |  | 15 |  | 16
16 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 16 |  |  | 16 |  | 17
17 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 17 |  |  | 17 |  | 18
18 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 18 |  |  | 18 |  | 19
19 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 19 |  |  | 19 |  | 20
20 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 20 |  |  | 20 |  | 21
21 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 21 |  |  | 21 |  | 22
22 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 22 |  |  | 22 |  | 23
23 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 23 |  |  | 23 |  | 24
24 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 24 |  |  | 24 |  | 25
25 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 25 |  |  | 25 |  | 26
26 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 26 |  |  | 26 |  | 27
27 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 27 |  |  | 27 |  | 28
28 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 28 |  |  | 28 |  | 29
29 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 29 |  |  | 29 |  | 30
30 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 30 |  |  | 30 |  | 31
31 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 31 |  |  | 31 |  | 32
32 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 32 |  |  | 32 |  | 33
33 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 33 |  |  | 33 |  | 34
34 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 34 |  |  | 34 |  | 35
35 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 35 |  |  | 35 |  | 36
36 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 36 |  |  | 36 |  | 37
37 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 37 |  |  | 37 |  | 38
38 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 38 |  |  | 38 |  | 39
39 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 39 |  |  | 39 |  | 40
40 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 40 |  |  | 40 |  | 41
41 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 41 |  |  | 41 |  | 42
42 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 42 |  |  | 42 |  | 43
43 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 43 |  |  | 43 |  | 44
44 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 44 |  |  | 44 |  | 45
45 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 45 |  |  | 45 |  | 46
46 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 46 |  |  | 46 |  | 47
47 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 47 |  |  | 47 |  | 48
48 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 48 |  |  | 48 |  | 49
49 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 49 |  |  | 49 |  | 50
50 | [5 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0% | --- |  | 0 |  |  | 1 | 1 | 1 | 1 | 50 |  |  | 50 |  | 51
| --- |  |  | -46234 | [6 empty] | #REF! |  |  | 0 | 4 |  |  |  | #N/A | 0 | [5 empty] | 1 | 1 |  |  |  |  | 0 | 52
Formulas:
Days Left = IF(ISBLANK([Due Date]),"",[Due Date]-TODAY())
Days Left = IF(ISBLANK([Task]),"",[Due Date]-TODAY())
Due Date = [Due Date]
Remove Completed Tasks

## Timeline
|  | Start Date | Start | Completed | Remaining | Overdue | Fill | End | Taskline Length
1 | Kaeser air comp. project | 2007-02-17 |  | 106 | 0 | 0 |  |  | 106
2 | TF Safeguarding Project | 2007-06-28 |  | 0 | 75 | 6898 |  |  | 6973
3 | Watch room upgrade | 2007-08-02 |  | 39.27 | 11.73 | 6887 |  |  | 6938
4 | KOS upgrade | 2007-08-13 |  | 124.8 | 70.2 | 6732 |  |  | 6927
5 |  | 2007-02-17 | [6 empty] | 0
6 |  | 2007-02-17 | [6 empty] | 0
7 |  | 2007-02-17 | [6 empty] | 0
8 |  | 2007-02-17 | [6 empty] | 0
9 |  | 2007-02-17 | [6 empty] | 0
10 |  | 2007-02-17 | [6 empty] | 0
11 |  | 2007-02-17 | [6 empty] | 0
12 |  | 2007-02-17 | [6 empty] | 0
13 |  | 2007-02-17 | [6 empty] | 0
14 |  | 2007-02-17 | [6 empty] | 0
15 |  | 2007-02-17 | [6 empty] | 0
16 |  | 2007-02-17 | [6 empty] | 0
17 |  | 2007-02-17 | [6 empty] | 0
18 |  | 2007-02-17 | [6 empty] | 0
19 |  | 2007-02-17 | [6 empty] | 0
20 |  | 2007-02-17 | [6 empty] | 0
21 |  | 2007-02-17 | [6 empty] | 0
22 |  | 2007-02-17 | [6 empty] | 0
23 |  | 2007-02-17 | [6 empty] | 0
24 |  | 2007-02-17 | [6 empty] | 0
25 |  | 2007-02-17 | [6 empty] | 0
26 |  | 2007-02-17 | [6 empty] | 0
27 |  | 2007-02-17 | [6 empty] | 0
28 |  | 2007-02-17 | [6 empty] | 0
29 |  | 2007-02-17 | [6 empty] | 0
30 |  | 2007-02-17 | [6 empty] | 0
31 |  | 2007-02-17 | [6 empty] | 0
32 |  | 2007-02-17 | [6 empty] | 0
33 |  | 2007-02-17 | [6 empty] | 0
34 |  | 2007-02-17 | [6 empty] | 0
35 |  | 2007-02-17 | [6 empty] | 0
36 |  | 2007-02-17 | [6 empty] | 0
37 |  | 2007-02-17 | [6 empty] | 0
38 |  | 2007-02-17 | [6 empty] | 0
39 |  | 2007-02-17 | [6 empty] | 0
40 |  | 2007-02-17 | [6 empty] | 0
41 |  | 2007-02-17 | [6 empty] | 0
42 |  | 2007-02-17 | [6 empty] | 0
43 |  | 2007-02-17 | [6 empty] | 0
44 |  | 2007-02-17 | [6 empty] | 0
45 |  | 2007-02-17 | [6 empty] | 0
46 |  | 2007-02-17 | [6 empty] | 0
47 |  | 2007-02-17 | [6 empty] | 0
48 |  | 2007-02-17 | [6 empty] | 0
49 |  | 2007-02-17 | [6 empty] | 0
50 |  | 2007-02-17 | [6 empty] | 0

## Reminders
|  | Reminder Control |  |  | Severity Levels
|  | Show tasks due in | 50 | days or less |  | P1
|  | Show overdue tasks | 1 |  |  | P2 | Yes
[6 empty] | P3 | No
low
Reminders
| Task | Reminder
1 | TF Safeguarding Project | This task was due 6898 days ago | -6898 | Task "TF Safeguarding Project" was due 6898 days ago
2 | Watch room upgrade | This task was due 6887 days ago | -6887 | Task "Watch room upgrade" was due 6887 days ago
3 | KOS upgrade | This task was due 6732 days ago | -6732 | Task "KOS upgrade" was due 6732 days ago
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Reports
Current Status |  |  | Employee: | Aziz Rawahi |  | (mu42663) |  |  |  | Calculated Cells
|  |  | Time: | 2026-07-31 14:14 | [5 empty] | Entered Values
Supervisor's Email Address
rawahix3@hotmail.com
|  | Tasks Not Started |  |  | Tasks In Progress |  |  |  | Tasks Overdue
|  | Task | Due Date | Priority | Task | Due Date | Progress | Priority | Task | Due Date | Progress | Priority
| 1 | TF Safeguarding Project | 2007-09-11 | P1 | Watch room upgrade | 2007-09-22 | 77% | P2 | TF Safeguarding Project | 2007-09-11 | 0% | P1
| 2 |  |  |  | KOS upgrade | 2008-02-24 | 64% | P0 | Watch room upgrade | 2007-09-22 | 77% | P2
| 3 | [7 empty] | KOS upgrade | 2008-02-24 | 64% | P0
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Submit Report

## Settings
Status |  |  | Priority
| --- | 1 |  | --- | 1 | ---
| Not Started | 2 |  | P0 | 2 | P0
| In Progress | 3 |  | P1 | 3 | P1
| Completed | 4 |  | P2 | 4 | P2
| Waiting Materials | 5 |  | P3 | 5 | P3
| Deferred | 6 |  |  | 6
|  | 7 |  |  | 7
|  | 8 |  |  | 8
|  | 9 |  |  | 9
Categories
| --- | 1
| P1 | 2
| P2 | 3
| P3 | 4
| Low Impact | 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21